## Requirements Traceability Matrix
CNV Enterprise Permitting & Licensing System - Requirements Traceability Matrix (RTM)
Prepared by: Sara Zhanturina ¦ Project: CNV Planning & Development ¦ Date: April 2026 ¦ Version: 1.0
BR # | Functional Area | Requirement Description | Priority (MoSCoW) | Status | Stakeholder | Strategic Link | BPMN Ref | Test Approach | Acceptance Criteria | Notes / Source
APPLICATION INTAKE
BR-01 | Application Intake | System SHALL provide an online portal for applicants to submit permit and licence applications without requiring in-person or paper submission | Must Have | Approved | Applicants / Planning | Connected City | To-Be: Submit via online portal | Functional + UAT | Applicant completes and submits application fully online; no paper form required | CNV Annual Report 2024 - digital-first service goal
BR-02 | Application Intake | System SHALL automatically validate application completeness at submission. Applicant cannot submit without required fields and documents | Must Have | Approved | Applicants / Planning | Prosperous City | To-Be: Auto-validate completeness | Automated + UAT | Incomplete submission triggers error message listing missing items; submission blocked | Addresses current manual completeness check process
BR-03 | Application Intake | System SHALL generate a unique application reference number upon successful submission and send automated confirmation to applicant | Must Have | Approved | Applicants | Connected City | To-Be: Submit via online portal | Automated | Reference number generated within 60 seconds of submission; confirmation email sent | Standard intake requirement
BR-04 | Application Intake | System SHALL support application types required by Bills 44, 46, and 47 (2024 provincial housing legislation), including SSMUH and TOD | Must Have | Approved | Applicants / Planning | City for People | To-Be: Submit via online portal | Regulatory | All Bill 44/46/47 application types available in portal drop-down | BC Housing legislation compliance - mandatory
BR-05 | Application Intake | System SHOULD provide a pre-submission requirements checklist so applicants understand what is needed before starting their application | Should Have | Proposed | Applicants | Prosperous City | To-Be: Submit via online portal | UAT | Checklist displays correct requirements for selected application type | Reduces incomplete applications
DEPT REVIEW WORKFLOW
BR-06 | Dept Review Workflow | System SHALL automatically route applications to relevant reviewing departments based on application type and configurable routing rules | Must Have | Approved | Planning / Engineering / Fire | Prosperous City | To-Be: Auto-route to departments | Automated + UAT | Application routed to correct departments within 1 business day of submission | Replaces current email referral process
BR-07 | Dept Review Workflow | System SHALL notify reviewing departments of new referrals and track review status in a shared dashboard visible to Planning staff | Must Have | Approved | Planning / Engineering / Fire | Connected City | To-Be: Review in dashboard | Functional | Dashboard shows real-time status of all referrals; Planning can see Engineering/Fire status | Addresses current lack of referral status visibility
BR-08 | Dept Review Workflow | System SHALL prevent a final decision from being recorded until all required departmental reviews are completed or explicitly waived | Must Have | Approved | Planning (Senior Planner) | Responsible Org | To-Be: Approve/waive review | Process | System blocks decision action until all reviews show Completed or Waived status | Process integrity control
BR-09 | Dept Review Workflow | System SHALL send automated reminders to reviewing departments when reviews are approaching or past their SLA target | Should Have | Proposed | Engineering / Fire | Prosperous City | To-Be: SLA monitoring | Automated | Reminder sent at 80% of SLA window; escalation at 100% | Reduces inter-dept delays
BR-10 | Dept Review Workflow | System SHOULD support Indigenous consultation tracking for applications in traditional territories of Squamish and Tsleil-Waututh Nations | Should Have | Proposed | Planning / Indigenous Relations | Reconciliation | To-Be: Review in dashboard | Functional | Consultation flag triggers on properties in traditional territories; status trackable | CNV Reconciliation commitment
APPLICANT COMMUNICATION
BR-11 | Applicant Communication | System SHALL provide applicants with real-time visibility into their application status through a self-service portal | Must Have | Approved | Applicants | Connected City | To-Be: Track status self-service | UAT | Applicant can log in and see current status, last action, and next step | Reduces inbound status calls to Planning staff
BR-12 | Applicant Communication | System SHALL send automated status update notifications to applicants at key milestones (received, review commenced, info required, decision issued) | Must Have | Approved | Applicants | City for People | To-Be: Track status self-service | Automated | Notification sent within 1 business day of each milestone event | Customer service standard
BR-13 | Applicant Communication | System SHOULD allow Planning staff to communicate with applicants through the system with all correspondence logged against the application | Should Have | Proposed | Planning / Applicants | Prosperous City | To-Be: Review in dashboard | Functional | Messages sent via system logged with timestamp and user ID | Audit trail requirement
BUSINESS LICENSING
BR-14 | Business Licensing | System SHALL support online business licence applications and annual renewals for CNV's approximately 7,000 registered businesses, with automated renewal reminders at 60 and 30 days before expiry | Must Have | Approved | Businesses / EcDev | Prosperous City | To-Be: Submit via online portal | Functional + UAT | Renewal reminders sent automatically; online renewal available 90 days before expiry | High volume - approx. 7,000 annual renewals
BR-15 | Business Licensing | System SHALL calculate applicable fees automatically based on business type, size, and location, aligned with CNV's Consolidated Fees and Charges Bylaw (July 2024) | Must Have | Approved | Finance / Businesses | Responsible Org | To-Be: Auto-generate decision letter | Automated | Fee calculated correctly for 10 test business scenarios across different categories | Revenue accuracy and compliance
BR-16 | Business Licensing | System SHOULD support the North Shore Inter-Municipal Business Licence regime as referenced in CNV's 2025 workplan | Should Have | Proposed | EcDev / Businesses | Prosperous City | To-Be: Submit via online portal | Functional | NSIMBL applications processed through same portal with inter-municipal routing | CNV 2025 workplan initiative
REPORTING
BR-17 | Reporting | System SHALL generate standard operational reports: applications by type/status, average processing time by permit category, SLA compliance rate, and revenue by type | Must Have | Approved | Planning / Finance / CAO | Responsible Org | To-Be: Generate reports | Functional | All 4 standard reports generate correctly with accurate data from test dataset | Replaces manual report compilation
BR-18 | Reporting | System SHALL support CNV's KPI framework (developed with KPMG 2024) by providing data exports aligned to the Municipal Reference Model | Should Have | Proposed | CAO / Planning | Responsible Org | To-Be: Generate reports | Integration | Data export matches MRM field mapping document; no manual transformation required | CNV KPMG engagement 2024
BR-19 | Reporting | System SHALL produce an annual permit activity report with data comparable to CNV's existing Annual Municipal Report statistics | Must Have | Approved | Planning / CAO | Open Organisation | To-Be: Generate reports | Functional | Annual report generated with permit counts, processing times, and revenue totals | Public accountability requirement
TECHNICAL / COMPLIANCE
BR-20 | Technical / Compliance | System SHALL comply with BC FOIPPA. All personal data must be stored in Canada per CNV Privacy Management Program (2024) | Must Have | Approved | IT / Legal | Safe & Secure | N/A - compliance | Security audit | Privacy Impact Assessment completed; data residency confirmed as Canada | Non-negotiable regulatory requirement
BR-21 | Technical / Compliance | System SHALL meet WCAG 2.1 AA accessibility standards. Required by CNV Accessibility Plan (in development 2025) | Must Have | Approved | IT / Applicants | City for People | N/A - compliance | Accessibility audit | Third-party WCAG 2.1 AA audit passes with zero critical failures | BC accessibility requirements
BR-22 | Technical / Compliance | System SHALL integrate with CNV's existing financial systems for fee collection and reconciliation, per the New Financial Framework (2024) | Must Have | Approved | Finance / IT | Responsible Org | To-Be: Auto-generate decision letter | Integration | Fee payments post correctly to financial system within same business day | Financial integrity requirement
BR-23 | Technical / Compliance | System SHOULD integrate with CNV's GIS platform to link permit applications to property parcels and enable spatial analysis of development activity | Should Have | Proposed | IT / Planning | Connected City | N/A - integration | Integration | Permit applications display on GIS map linked to correct parcel | Supports spatial analysis of development activity - GIS integration

## Summary Dashboard
RTM Summary Dashboard — CNV Enterprise Permitting & Licensing System
Priority | Count | % of Total
Must Have | 16 | 69.57%
Should Have | 7 | 30.43%
Could Have | 0 | 0%
TOTAL | 23
Status | Count
Approved | 16
Proposed | 7
In Review | 0
Functional Area | # Requirements
Application Intake | 5
Dept Review Workflow | 5
Applicant Communication | 3
Business Licensing | 3
Reporting | 3
Technical / Compliance | 4

## Legend & Guide
Legend & Guide — How to use this RTM
PRIORITY
Must Have | Core system functionality — required for go-live. Non-negotiable.
Should Have | Important but not critical for initial launch. Target Phase 2.
Could Have | Nice to have — include if time and budget allow.
STATUS
Approved | Requirement confirmed and baselined by stakeholders.
Proposed | Requirement drafted — awaiting stakeholder sign-off.
In Review | Under discussion — may be modified or deferred.
BPMN REF
As-Is ref | Reference to current state process step in BPMN_AsIs diagram.
To-Be ref | Reference to future state process step in BPMN_ToBe diagram.
N/A | Non-process requirement (technical, compliance, integration).
HOW TO USE
Filter by Priority | Use Excel filter on Column D to view Must Have requirements only.
Filter by Area | Use Excel filter on Column B to view requirements by department.
Filter by Status | Use Excel filter on Column E to track sign-off progress.
Track progress | Update Column E status as requirements are reviewed and approved.